## Sheet1
Product Backlog
Features | User Stories | Planned Sprint | Estimated Hours | Assignation | prefrences | Recover Assignation
Search Restaurants | I want to search for a desired store fit to my order | Sprint 2 | 15 | Mahmoud , Mohamed | high | Shrief
View Menu | I need to see the menu of that store | Sprint 2 | 10 | Heba , shrief | high | Ahmed
|  | Total hours | 25
Capacity | Sprint 2 capacity assigned to four developer whose names were mentioned above with their substitutes for any urgent cases