## Sheet1
Sprints Planning
Features | User Stories | Planned Sprint | Estimated Hours | Assignation | prefrences
1 Create Account | I need to creat my account as a user | Sprint 1 | 5 | shrief | high
2 View Restaurants | I welling to see availabe opening stores | Sprint 1 | 20 | Mohamed , Ahmed | high
3 Search Restaurants | I want to search for a desired store fit to my order | Sprint 2 | 15 | Mahmoud , Mohamed | high
4 View Menu | I need to see the menu of that store | Sprint 2 | 10 | Heba , shrief | high
5 Add to Cart | I need to add desired item to my cart | Sprint 3 | 20 | Ahmed , Mahmoud | high
6 Purchase | I want to purchase an item | Sprint 4 | 5 | Heba | high
7 Restaurant views order | As a store user I need to view my customers orders | Sprint 4 | 10 | Mohamed , Ahmed | high
8 Restaurant marks order as delivered | As a store user I need to show my customers that I delivered their order | Sprint 5 | 28 | Mahmoud , Shrief | high